## Participants
Inspection Roles
No | Group Member | Roles | Comment
1 | Nguyen quang thong | Moderator
2 | Mai Hoang Tung | Inspector
3 | Tran Quoc Hoang | Inspector
4 | Pham Ngoc Trung | Inspector
5 | Phan Quang Trung | Inspector

## Schedules
Inspection Schedule
No | Task | Task owner | Start time | End time | Comment
1 | Review PROJETC PLAN DOCUMENT | Pham Ngoc Trung | 26/01/2024 | 27/01/2024
2 | Review SOFTWARE REQUIREMENT SPECIFICATION DOCUMENT | Nguyen Quang Thong, Tran Quoc Hoang | 27/01/2024 | 27/01/2024
3 | Review DEFINDED PROCESS DOCUMENT | Pham Ngoc Trung | 26/01/2024 | 27/01/2024
4 | Review CODE | Nguyen Quang Thong, Tran Quoc Hoang, Pham Ngoc Trung, Mai Hoang Tung, Phan Quang Trung | 29/01/2024 | 30/01/2024
5 | Review TEST CASE | Mai Hoang Tung | 30/01/2024 | 30/01/2024
6 | Review USER INTERFACE DESIGN DOCUMENT | Phan Quang Trung | 28/01/2024 | 28/01/2024

## Materials
Inspection Material
No | Tool/Material | Quantity | Comment
1 | Apache NetBeans | 5
2 | Word | 5
3 | Excel | 1
4 | Laptop | 5